## Team
SSW-555 Group G — GEDCOM Project
Name | Role | GitHub Username
Kevin Hyun | Developer | Hyunguy
Maxx Bobkov | Developer | mbobkov26
Jalen Thompson | Developer | JalenT122
GitHub Repository: | github.com/Hyunguy/ssw555-gedcom-project

## Backlog
Story ID | Description | Sprint | Owner | Est. Size (LOC) | Est. Time (min) | Actual Size (LOC) | Actual Time (min) | Status
US01 | Dates before current date | 1 | Kevin Hyun | 20 | 30 | 18 | 25 | Complete
US03 | Birth before death | 1 | Kevin Hyun | 15 | 20 | 14 | 18 | Complete
US04 | Marriage before divorce | 1 | Maxx Bobkov | 15 | 20 | 16 | 22 | Complete
US05 | Marriage before death | 1 | Maxx Bobkov | 20 | 30 | 19 | 28 | Complete
US07 | Less than 150 years old | 1 | Jalen Thompson | 15 | 25 | 15 | 20 | Complete
US08 | Birth before marriage of parents | 1 | Jalen Thompson | 20 | 35 | 21 | 33 | Complete
US02 | Birth before marriage | 2 | Kevin Hyun | 15 | 20 | 8 | 12 | Complete
US06 | Divorce before death | 2 | Kevin Hyun | 15 | 20 | 9 | 13 | Complete
US09 | Birth before death of parents | 2 | Maxx Bobkov | 25 | 45 | 23 | 40 | Complete
US10 | Marriage after 14 | 2 | Maxx Bobkov | 20 | 30 | 18 | 27 | Complete
US12 | Parents not too old | 2 | Jalen Thompson | 25 | 45 | 24 | 42 | Complete
US13 | Siblings spacing | 2 | Jalen Thompson | 25 | 45 | 26 | 44 | Complete
US14 | Multiple births fewer than 5 | 3 | Kevin Hyun | 10 | 20 | 19 | 30 | Complete
US15 | Fewer than 15 siblings | 3 | Kevin Hyun | 10 | 20 | 13 | 20 | Complete
US16 | Male last names | 3 | Maxx Bobkov | 10 | 20 | 9 | 16 | Complete
US17 | No marriages to descendants | 3 | Maxx Bobkov | 12 | 25 | 25 | 37 | Complete
US18 | Siblings should not marry | 3 | Jalen Thompson | 10 | 20 | 11 | 22 | Complete
US21 | Correct gender for role | 3 | Jalen Thompson | 8 | 15 | 8 | 14 | Complete
US19 | First cousins should not marry | 4 | Kevin Hyun | 30 | 55 |  |  | Planned
US22 | Unique IDs | 4 | Kevin Hyun | 15 | 25 |  |  | Planned
US23 | Unique name and birth date | 4 | Maxx Bobkov | 20 | 30 |  |  | Planned
US24 | Unique families by spouses | 4 | Maxx Bobkov | 20 | 35 |  |  | Planned
US25 | Unique first names in families | 4 | Jalen Thompson | 20 | 30 |  |  | Planned
US29 | List deceased | 4 | Jalen Thompson | 15 | 20 |  |  | Planned

## Burndown
Sprint | Date | Remaining Stories | Story Velocity | Total LOC | Total Min | Code Velocity (LOC/hr)
Start | 2026-06-15 | 24 |  | 0 | 0
Sprint 1 | 2026-06-21 | 18 | 6 | 103 | 146 | 42.3288
Sprint 2 | 2026-07-05 | 12 | 6 | 211 | 324 | 36.4045
Sprint 3 | 2026-07-19 | 6 | 6 | 296 | 463 | 36.6906

## Sprint1
Sprint 1 (6/15/2026 - 6/21/2026)
Story ID | Description | Owner | Est. Size (LOC) | Est. Time (min) | Actual Size (LOC) | Actual Time (min) | Status
US01 | Dates before current date | 1 | Kevin Hyun | 20 | 30 | 18 | 25 | Complete
US03 | Birth before death | 1 | Kevin Hyun | 15 | 20 | 14 | 18 | Complete
US04 | Marriage before divorce | 1 | Maxx Bobkov | 15 | 20 | 16 | 22 | Complete
US05 | Marriage before death | 1 | Maxx Bobkov | 20 | 30 | 19 | 28 | Complete
US07 | Less than 150 years old | 1 | Jalen Thompson | 15 | 25 | 15 | 20 | Complete
US08 | Birth before marriage of parents | 1 | Jalen Thompson | 20 | 35 | 21 | 33 | Complete
Sprint Review
Keep Doing:
- Committing to GitHub daily
- Writing tests before submitting
Stop Doing:
- Waiting until the deadline day to fill in the Sprint Report

## Sprint2
Sprint 2 (6/22/2026 - 7/5/2026)
Story ID | Description | Owner | Est. Size (LOC) | Est. Time (min) | Actual Size (LOC) | Actual Time (min) | Status
US02 | Birth before marriage | 2 | Kevin Hyun | 15 | 20 | 8 | 12 | Complete
US06 | Divorce before death | 2 | Kevin Hyun | 15 | 20 | 9 | 13 | Complete
US09 | Birth before death of parents | 2 | Maxx Bobkov | 25 | 45 | 23 | 40 | Complete
US10 | Marriage after 14 | 2 | Maxx Bobkov | 20 | 30 | 18 | 27 | Complete
US12 | Parents not too old | 2 | Jalen Thompson | 25 | 45 | 24 | 42 | Complete
US13 | Siblings spacing | 2 | Jalen Thompson | 25 | 45 | 26 | 44 | Complete
Sprint Review
Keep Doing:
- Pair programming on shared logic (US06)
- Testing each story with unittest before merging
Stop Doing:
- Splitting date parsing logic across files, which caused merge conflicts

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US14 | Multiple births <= 5 | kh | Completed | 10 | 20 | 19 | 30 | 7/19/2026
T14.01 | Get family record
T14.02 | Get child records
T14.03 | Get birth records for siblings
T14.04 | Check birthdates for same date
US15 | Fewer than 15 siblings | kh | Completed | 10 | 20 | 13 | 20 | 7/19/2026
T15.01 | Get family record
T15.02 | Get child records
T15.03 | Flag if # of children >= 15
US16 | Male last names | mb | Completed | 10 | 20 | 9 | 16 | 7/19/2026
T16.01 | Get family record
T16.02 | Get all male members of family
T16.03 | Check all last names match
US17 | No marriages to descendants | mb | Completed | 12 | 25 | 25 | 37 | 7/19/2026
T17.01 | Get family record
T17.02 | Get both parent records
T17.03 | Get all marriage records for descendants
T17.04 | Flag if any spouse is a descendant
US18 | Siblings should not marry | jt | Completed | 10 | 20 | 11 | 22 | 7/19/2026
T18.01 | Get family record
T18.02 | Get child records
T18.03 | Get marriage records for children
T18.04 | Flag marriage to sibling
US21 | Correct gender for role | jt | Completed | 8 | 15 | 8 | 14 | 7/19/2026
T21.01 | Get family record
T21.02 | Get parent records
T21.03 | Flag if husband not male or wife not female
Sprint #3 Review
Keep Doing
Divide user stories into small trackable tasks before coding
Link code to user story IDs in commits
Maintain format for error signature across user stories
Run parser end-to-end after each story
Communicate over group chat to coordinate ownership
Stop doing
Not sharing useful libraries
Communicating at late hours rather than earlier

## Sprint4
Sprint 4 (7/20/2026 - 8/2/2026) - Planned
Story ID | Description | Owner | Est. Size (LOC) | Est. Time (min) | Actual Size (LOC) | Actual Time (min) | Status
US19 | First cousins should not marry | 4 | Kevin Hyun | 30 | 55 |  |  | Planned
US22 | Unique IDs | 4 | Kevin Hyun | 15 | 25 |  |  | Planned
US23 | Unique name and birth date | 4 | Maxx Bobkov | 20 | 30 |  |  | Planned
US24 | Unique families by spouses | 4 | Maxx Bobkov | 20 | 35 |  |  | Planned
US25 | Unique first names in families | 4 | Jalen Thompson | 20 | 30 |  |  | Planned
US29 | List deceased | 4 | Jalen Thompson | 15 | 20 |  |  | Planned